## Slide 1
Claims Management: Insights from Case Law
www.aluko-oyebode.com
November 2022
Ngo-Martins Okonmah, MCIArb
Partner, Aluko & Oyebode

## Slide 2
Notice Provision under FIDIC 2017 – So what has changed?
Under the FIDIC 1999, a contractor with a claim is merely required to give Notice to the Engineer describing the event or circumstance giving rise to the claim, which notice must be giving within 28 days.
The failure to issue a Notice of Claim within the 28 days period would result in a loss of entitlement.
However, the FIDIC 2017 introduced two notices to be given in order to be entitled to make a claim.
First, is a Notice of Claim under sub-clause 20.2.1 to be given “… no later than 28 days after the claiming Party became aware or should have become aware of the event or circumstances”
Second is a Fully Detailed Claim under sub-clause 20.2.4 to be given “within either 84 days after the claiming Party became aware, or should have become aware, of the event or circumstance giving rise to the Claim…”
A fully detailed claim means a submission which includes a statement of the contractual and/or other legal basis of the claim see Sub-clause 20.2.4
1
2
3
4
5
6

## Slide 3
Notice Provision under FIDIC 2017 – So what has changed?
Both the Notice of Claim and the submission of a Fully Detailed Claim are express time bar under the contract, as the failure to give either notice will result in a loss of entitlement.
Is a party precluded from pursuing a claim on a different contractual and/or legal basis from that stated in the Notice of Claim given to the Engineer in a subsequent referral to DAAB or arbitration?
Question
This issue was considered in Maeda Corporation v. Bauer Hong Kong Ltd [2020] HKCA 830, a recent case arising from the construction of the Hong Kong to Guangzhou Express Rail Link connecting Hong Kong to mainland China.
Case Under Review

## Slide 4
Notice Provision under FIDIC 2017 – So what has changed?
In this case, Maeda was appointed main contractor for the tunnelling aspects of the project and subcontracted certain diaphragm wall work to Bauer. During the course of the works, Bauer encountered unforeseen ground conditions and claimed additional payment from Maeda. Bauer initially claimed that the additional work required to overcome the changed ground conditions amounted to a variation under the subcontract and relied solely on the variation clause in the sub-contract as the contractual/legal basis for the claim. However, by the time the claim had reached arbitration, Bauer had expanded its grounds of claim to include the clause under the sub-contract dealing with unforeseen ground conditions.
The claims notification provision under the subcontract required Bauer to give a notice of claim within 14 days of the event or matter giving rise to the claim. A further notice, described as a condition precedent to entitlement, was to be given 28 days later setting out the ‘contractual basis together with full detailed particulars and the evaluation of the claim’. The contract also made clear that Bauer would have no right to any additional payment unless the claims notification procedure had been ‘strictly complied with’.
It was common ground that Bauer’s initial notices of claim referred only to the variation provision of the subcontract as the basis for the claim. Consequently, Maeda argued that Bauer’s claim under the unforeseen ground conditions clause was therefore barred.
The arbitrator rejected this challenge, noting that it was unrealistic to expect a party to finalise its legal case within the period provided for notification of a claim. It was sufficient in his view for the factual basis of a claim to be communicated in the notice.

## Slide 5
On appeal to the High Court, the court overturned the decision of the Arbitrator finding that the language of the contract was clear and unambiguous in requiring Bauer to strictly comply with the notice provision and therefore Bauer was precluded from advancing its claims on grounds other than those relied in its Notice of Claim to the Engineer. Bauer appealed to the Court of Appeal and the Court of Appeal upheld the decision of the High Court.
The Court of Appeal held that the notice provisions should be given its clear and literal meaning, rather than the purposive approach adopted by the Arbitrator. The Court recognised three commercial reasons for strictly requiring the contractual basis of a claim to be notified at the outset as (i) it would allow Maeda as the contractor to investigate Bauer’s claim; (ii) it would provide parties with finality, in ensuring new claims based on different contractual provisions are not advanced years down the line; and (iii) it would allow Maeda to identify whether Bauer’s claim needed to be ‘passed up the line’ to Maeda’s ultimate employer.
Do you agree with the decision of the Court of Appeal?
Notice Provision under FIDIC 2017 – So what has changed?

## Slide 6
Practical Implications/Lessons for Parties
Parties should pay close attention to notification provisions, including whether they are identified as condition precedents.
When presenting a claim on alternative basis, there will be a need to update the claim particulars and quantum periodically by reference to these alternative bases of claim, in addition to the primary basis of claim, given that the compensation entitlement may be different depending on the basis of the claim advanced; and
Project Legal Support
When first notifying claims, consider taking a broad approach to identifying the potential bases of a claim. Even if one source of contractual entitlement is identified as the primary basis of a claim, consider presenting alternative basis.
Seek legal advice, particularly for significant claims, at the very inception of the claim, to assess all possible foundations for the claim and prepare notices that specify wide range of legal and contractual bases for the claim.
Notice Provision under FIDIC 2017 – So what has changed?

## Slide 7
Set-Off Rights and Counter Claims – Let Employer Beware!
3
5
4
2
1
6
Under sub-clause 2.5 FIDIC Red and Yellow Books 1999, the Employer is to give notice if it considers itself to be entitled to any payment from the Contractor in connection with the contract. Thereafter, the Engineer shall proceed to agree or determine the claim in accordance with sub-clause 3.5.
This question was considered by the Privy Council in NH International (Caribbean) Limited v National Insurance Property Development Company Limited (Trinidad and Tobago) [2015] UKPC 37.
Question – Is an Employer precluded from claiming payment in subsequent DAB or arbitration proceedings if it fails to give notice in accordance with sub-clause 2.5?
Afterwards, the amount may be included as a deduction in the contract price and payment certificate. “The Employer shall only be entitled to set off against or make any deduction from an amount certified in a payment certificate, or to otherwise claim against the Contractor, in accordance with this sub-clause”. See sub-clause 2.5
In this case, the Contractor and Employer entered into a contract based on the FIDIC Redbook for the construction of a hospital in Tobago. The project started in March 2003 and had a completion date of March 2005. The contractor suspended the works on 23 September 2005 and terminated the contract on 3 November 2006.
If an Employer sets off a sum of money in a way that it is not entitled to do under the contract, it is likely to impact the Contractor’s cash flow and may give the Contractor a right to suspend Works or terminate the contract.

## Slide 8
Set-Off Rights and Counter Claims – Let Employer Beware!
In arbitration proceedings commenced by the Contractor, the Contractor claimed damages arising from the termination of the contract and the Employer submitted various counter claims.
The Contractor only became aware of the counterclaims during the arbitration proceedings given that the Employer had failed to deliver a notice as required by sub-clause 2.5 at any stage following the conclusion of the contract.
The Contractor contended that the employer was precluded from raising any counter claim in the arbitration proceedings given that the Employer failed to give notice as required by sub-clause 2.5. The arbitrator rejected the Contractor’s contention in this regard and held that ‘clear words are required to exclude common law rights of set-off and/or abatement of legitimate cross claims’. The arbitrator found that sub-clause 2.5 did not bar the Employer’s counterclaims because the words were not sufficiently clear to exclude common law right of set off.
That decision was upheld on appeal to the High Court and the Court of Appeal. In particular, the High Court held that while the last paragraph of clause 2.5 prohibits the Employer from setting off any sum against amount certified in a Payment Certificate, it does not prevent the Employer from exercising his right of set-off in any other way, and in particular, against amounts that are not certified.

## Slide 9
However, the Privy Council overturned the decision. It held that the last paragraph of sub-clause 2.5 operates to exclude the Employer from exercising set off right against both amount in a payment certificate and uncertified payments such as in subsequent DAB or arbitration proceedings and this is because of the use of the underlined words “The Employer shall only be entitled to set off against or make any deduction from an amount certified in a payment certificate, or to otherwise claim against the Contractor, in accordance with this sub-clause”.
The Court found that the purpose of sub-clause 2.5 is to ensure that claims which an Employer wishes to raise, whether or not they are intended to be relied on as set-offs or cross claim, should not be allowed unless they have been the subject of a notice, which must be given as soon as practicable; and that if the Employer were permitted to rely on claims which were first notified in DAB or arbitration, then the requirement to given notice to the Engineer would be defeated.
Do you agree with the decision of the Privy Council?
Set-Off Rights and Counter Claims – Let Employer Beware!

## Slide 10
Practical Implications/Lessons for Employers
This is not a FIDIC 1999 problem, as FIDIC 2017 contains a clearer language in sub-clause 20.2.7 that operates to exclude the right of set off in the absence of notice. See Sub-clause 20.2.7. Both users of FIDIC 1999 and 2017 should beware!
Notices must be timely and particularized otherwise Employers may be precluded from making a claim. Note – the Privy Council did not define “as soon as practicable”?
Seek legal advice while the project is ongoing and particularly before making deductions against payment certificates.
Employers should ensure compliance with the notice provision under sub-clause 2.5 in order not to lose their entitlement to claim in subsequent DAB or arbitral proceedings. Notices must be timely and substantiated with particulars – refer to some war stories?
Employers may wish to amend the provisions of sub-clause 2.5 so that nothing in sub-clause 2.5 is construed as preventing any right of set off or cross claims – any example?
Set-Off Rights and Counter Claims – Let Employer Beware!

## Slide 11
Interim Payment Certificates – Why the Employer must be careful?
Payment Provisions
FIDIC Silver Book
FIDIC Red and Yellow
FIDIC Red and Yellow
FIDIC Red and Yellow
FIDIC Silver Book
FIDIC Silver Book
Question
There is a substantial difference between the payment provisions of the FIDIC 1999 & 2017 Red and Yellow Books compared to the FIDIC Silver Book.
Under the FIDIC Red and Yellow Books, the Contractor submits an application for payment pursuant to sub-clause 14.3.
Thereafter, the Engineer issues an interim payment certificate stating the amount which the Engineer ‘fairly’ determines to be due to the Contractor - see sub-clause 14.6.
Under sub-clause 14.7, the Employer is required to pay the Contractor the amount certified in each interim payment certificate.
However, the FIDIC Silver Book requires the Contractor to submit an application for payment to the Employer.
Upon receipt of the payment application, the Employer is required under sub-clause 14.6 to give notice to the Contractor within 28 days of any item in the payment application it disagrees with.
Under sub-clause 14.7, the Employer is to pay the contractor the amount which is due in respect of each statement.
Do claims in a payment application become due and payable as a result of the Employer’s failure to notify the contractor on items of disagreement in the payment application within 28 days?

## Slide 12
Interim Payment Certificates – Why the Employer must be careful?
This question was considered by the Supreme Court of Queensland in Sedgman South Africa (Pty) Ltd Ors v. Discovery Copper Botswana (Pty) Ltd [2013] QSC 105 where Sedgman, the contractor, and Discovery, the employer, entered into a USD90million EPC contract for the engineering, design, testing, procurement, construction and commissioning of the Boseto Copper Plant in Botswana, Southern Africa. The contract which was governed by the law of Queensland was based on the FIDIC Silver Book contract.
An interim payment claim for USD20million was served under sub-clause 14.3 on the Employer. Sub-clause 14.6 required the Employer to give notice within 7 days if it disagreed with any item in the application for payment. The Employer failed to give the notice within 7 days and did not contest the application until 14 days later.
The issue for the court was whether the Employer’s failure to serve a notice caused the interim payment claim to become a debt due and payable. The Employer denied that the failure to serve its notice had such effect and argued that the commencement of court proceedings was an attempt to by-pass the dispute resolution and arbitration clause in the contract. The Contractor argued that there could be no genuine dispute to the debt in light of Employer’s failure to give notice.

## Slide 13
The Court dismissed the Contractor’s application for payment holding that there was a genuine dispute which was appropriate for determination under the dispute resolution provision and that the Contractor’s interpretation of the contract was wrong. It held that the contract did not entitle the Contractor to be paid the sum which they claim simply because there was no response to their claim within the period stipulated in the contract.
The Court concluded that sub-clause 14.6 had to be read in the context of the whole contract and that if the Contractor’s contention were correct, it would mean that the operation of the various clauses of the contract to determine claim and variations would be displaced by the operation of sub-clause 14.6. In other words, if the Contractor included a claim in his application for payment which was inconsistent with, for example, a DAB’s determination, and the Employer did not give notice of disagreement, the outcome would be that the DAB’s determination would be displaced.
Interim Payment Certificates – Why the Employer must be careful?

## Slide 14
Practical Implications/Lessons for Employer
Interim Payment Certificates – Why the Employer must be careful?
Under the Silver Book, there is no requirement to issue interim payment certificate. The employer merely pay the amount which is due in respect of each statement.
Unlike the Silver Book, the Red and Yellow Books require the employer to pay to the contractor ‘amount certified in each interim payment certificate’ by the engineer. In other words, certified amounts are as good as cash.
Extreme care must be given in the certification of claims, as certified claims must be paid. Failing which, it may form a ground for suspension or termination of the contract by the Contractor - sub-clause 16.2(c) – any example?
Be warry of illegitimate claims by Contractor e.g. setting up a loss and expense claims as a variation claim in a payment application – any example?
Dealing with undue commercial pressure by Contractor – e.g., concessions should be without prejudice; consider paying unfulfilled milestones as advance payment; ensure Contractor sign off on measured works if the measurement is at variance with the payment application etc.
Endeavour to comply with the notice provision should you wish to set off against payment certificate or assert claims in DAB or arbitration.